## Slide 1
ALDER RIDGE MECHANICAL
PM WORKING COPY
Weekly Major Jobs Review
Schedule, labor, procurement, commercial position and cash milestones
June 29, 2026
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]

## Slide 2
WEEKLY MAJOR JOBS REVIEW
PM WORKING COPY
June 29, 2026
2
Portfolio heat map
01
Sixteen active / closeout projects
02
Schedule and access constraints
03
Estimate confidence
04
Cash and billing milestones
JOBS REVIEWED
16
PM status is operational evidence, not posted accounting data.
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]

## Slide 3
WEEKLY MAJOR JOBS REVIEW
PM WORKING COPY
June 29, 2026
3
Eastbank data-center expansion
CONTRACT
$11.6m
Receipt timing remains a treasury judgment supported by owner evidence.
01
Procurement-heavy cost profile
02
Owner funding draw timing
03
Lien-waiver dependency
04
Controls integration milestone
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]

## Slide 4
WEEKLY MAJOR JOBS REVIEW
PM WORKING COPY
June 29, 2026
4
Cascade Health ambulatory pavilion
PENDING PRICE
$382k
01
Night-shift premium exposure
02
Pending PCO documentation
03
Occupied-space phasing
04
Billing support
Probable cost is included in EAC; pending revenue is excluded.
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]

## Slide 5
WEEKLY MAJOR JOBS REVIEW
PM WORKING COPY
June 29, 2026
5
Northline cold storage
01
Backcharge dispute
02
Subcontractor response
03
Rework productivity
04
Remaining closeout
RECOVERY CLAIM
$185k
Unaccepted recovery is not netted against forecast cost.
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]

## Slide 6
WEEKLY MAJOR JOBS REVIEW
PM WORKING COPY
June 29, 2026
6
Columbia biologics closeout
OPEN AR AT RISK
$1.2m
Closeout receipts remain outside July base cash until evidence improves.
01
Validation package
02
Retainage
03
Customer dispute
04
Warranty transition
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]

## Slide 7
WEEKLY MAJOR JOBS REVIEW
PM WORKING COPY
June 29, 2026
7
Decisions and follow-up
OPEN ACTIONS
12
01
EAC owner responses
02
Commercial notices
03
Billing actions
04
Collection escalations
Finance reconciles final PM updates to system cost and billing after cutoff.
Notes: [Sources]
- environment/seed/sources/Shared/Operations/Project Reviews/weekly top jobs review - 6.29 PM copy.pptx
[/Sources]