## READ ME first
June WIP — risk-case review copy
Controller working file created 7/1/26 8:47am ¦ not a posted close schedule
Purpose | Refresh the four judgment-heavy jobs and document the controller's June review.
Posted actuals | Current contract, cost and billings reconcile to the company accounting records through 2026-06-30.
PM ETC | Use the latest PM submission before applying any finance adjustment.
Prior close | Use the final May WIP file for the prior-close margin baseline.
Policy | Apply the signed WIP policy to pending revenue, probable cost and disputed recoveries.
Review threshold | Flag margin movement greater than 100 basis points, forecast losses and any claim or backcharge netted in the PM forecast.
Audit trail | State the commercial treatment, rationale and controlling support for each project.
Status | WORKING / REVIEW — blank calculation columns are intentional.
Sign-off | Controller review required before values are copied into the close schedule.
Control — project rows
Control — named evidence rows
Control — blank formula cells
Decision bridge | Compare the PM and policy-adjusted close cases, quantify each margin impact and document the release decision.
Control — blank decision-bridge formulas

## Risk Review
June project estimate risk review
Blue cells require a current-source refresh, referenced finance formula or documented review conclusion
Project ID | Project | Current contract | Posted cost to date | PM ETC | Finance ETC adjustment | Close ETC | EAC | % complete | Earned revenue | Billings to date | Contract asset | Contract liability | Total est. margin | Margin % | May close margin % | June movement (bps) | Controller review | Commercial treatment / rationale | Controlling support
ARM-2318 | Columbia Biologics Clean Utilities
ARM-2409 | Northline Cold Storage Expansion
ARM-2417 | Cascade Health Ambulatory Pavilion
ARM-2506 | Eastbank Data Hall Cooling Expansion
TOTAL / CONTROL
CONTROLLER DECISION BRIDGE
Project ID | PM case EAC | PM case margin | Close case EAC | Close case margin | Margin impact | Pending revenue included? | Review required? | Close disposition | Required follow-up | Policy | Commercial support
ARM-2318
ARM-2409
ARM-2417
ARM-2506
DECISION CONTROL
Aggregate PM case margin |  | Aggregate close case margin |  | Aggregate margin impact
Pending commercial revenue included? |  | Review-required count |  | Largest overlay
Review queue
Close release decision
Policy basis

## Evidence Map
Risk-case evidence map
Paths are intentionally messy because they mirror the active shared-drive close folder
Project | Forecast evidence role | Commercial evidence role | Support clue | Accounting population | Policy question | Reviewer note
ARM-2318 | Latest consolidated June PM submission | Current commercial master / retest item | PM comment and commercial backup; no standalone packet retained | Current project summary through 6/30 | Can a recovery be recognized, and what unavoidable retest cost remains? | Closeout evidence incomplete
ARM-2409 | Latest consolidated June PM submission | Current commercial master / concrete backcharge | Draft project-numbered backcharge packet in commercial support | Current project summary through 6/30 | Can a disputed recovery be netted against ETC? | Concrete trade has not accepted
ARM-2417 | Latest consolidated June PM submission | Current commercial master / night-shift directive | Owner correspondence and field-direction packet | Current project summary through 6/30 | How should unexecuted revenue and probable after-hours cost be treated? | Owner directive not executed
ARM-2506 | Latest consolidated June PM submission | Current commercial master / design bulletin | Project-numbered design-bulletin cost estimate | Current project summary through 6/30 | How should technical direction without executed price be treated? | Technical direction only