## Project Status
Q2 project execution status
Approved operations review status as of June 30, 2026
Project ID | Current execution status | On plan | Status basis
ARM-2318 | Recovery plan | FALSE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2403 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2409 | Recovery plan | FALSE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2412 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2417 | Recovery plan | FALSE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2421 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2501 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2506 | Recovery plan | FALSE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2510 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2514 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2518 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2522 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2526 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2602 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2605 | Recovery plan | FALSE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
ARM-2608 | On plan | TRUE | 6/26 operations review; schedule, labor productivity, procurement and commercial status
Control | Result
Project status rows | 16
Recovery-plan rows | 5

## Review Protocol
Q2 field rework review protocol
Approved for the June 30 operations review
Order | Review element | Approved definition | Application note
1 | Population | Approved project-coded timecards dated April 1 through June 30, 2026 | Exclude service work orders, rejected time, and unapproved time
2 | Rework numerator | Approved project time coded to 06-300, Rework and Quality Correction | Summarize April, May, June, and Q2 by project
3 | Project-hour denominator | All approved project-coded hours across all cost codes for the same Q2 dates | Use project hours, not department payroll hours or rework hours alone
4 | Rework intensity | Q2 approved 06-300 hours divided by Q2 approved project hours | Calculate for each of the three highest-rework projects
5 | Recovery-plan priority | Assign first to a top-three project whose current execution status is Recovery plan | Execution status takes precedence over trend and intensity
6 | Worsening-trend watch | Among the remaining top-three projects, flag a project when April rework is below May and May is below June | Apply after the recovery-plan priority
7 | Highest-intensity root-cause review | Among the remaining top-three projects, assign the project with the highest rework intensity | Apply after recovery-plan and worsening-trend assignments
8 | One follow-up per project | Apply the three follow-up rules in order and do not assign more than one follow-up to the same project | Escalate any tie to VP Operations rather than inventing a tiebreaker
Control | Result
Protocol rows | 8
Follow-up rules | 3