## Submission Register
June 2026 Project Forecast Submissions
Snapshot exported 2026-06-29 17:30 PT ¦ Operations Finance working file
Project ID | Project | Project Manager | Submitted At | Confidence | Forecast ETC | Current Cost Budget | PM Comment | Submission Status
ARM-2318 | Columbia Biologics Clean Utilities | Maya Chen | 2026-06-27 15:15 | Medium | 173800 | 7271000 | Forecast based on CV-2318-06 and open PO-2318-102. | Received
ARM-2403 | Riverton Civic Center HVAC Renewal | Elliot Marks | 2026-06-27 18:15 | High | 892000 | 5109000 | Current field plan and committed buyout reflected. | Received
ARM-2409 | Northline Cold Storage Expansion | Priya Raman | 2026-06-28 16:15 | Low | 584000 | 4321000 | Forecast refreshed in the weekly project review and submitted 2026-06-28. | Received - review not started
ARM-2412 | OSU Kelley Engineering Lab Ventilation | Elliot Marks | 2026-06-26 17:15 | High | 947000 | 4083000 | Current field plan and committed buyout reflected. | Received
ARM-2417 | Cascade Health Ambulatory Pavilion | Maya Chen | 2026-06-26 18:15 | Low | 3048000 | 7970000 | Forecast based on phasing Rev 5 and open commitments through 6/24. | Received - review not started
ARM-2421 | Juniper Hotel Boiler Plant Replacement | Lucas Bennett | 2026-06-25 16:15 | High | 31000 | 1755000 | Current field plan and committed buyout reflected. | Received
ARM-2501 | PDX Concourse E Controls Retrofit | Sofia Alvarez | 2026-06-25 16:15 | High | 914000 | 2624000 | Current field plan and committed buyout reflected. | Received
ARM-2506 | Eastbank Data Hall Cooling Expansion | Priya Raman | 2026-06-25 17:15 | Low | 4731000 | 8722000 | Forecast based on IFC package E-18 and commitments through 6/24. | Received - review not started
ARM-2510 | Hawthorne Yard Mixed-Use Mechanical | Maya Chen | 2026-06-24 15:15 | High | 3284000 | 5968000 | Current field plan and committed buyout reflected. | Received
ARM-2514 | Redmond Unified Schools Phase 2 | Lucas Bennett | 2026-06-28 15:15 | High | 1492000 | 5529000 | Current field plan and committed buyout reflected. | Received
ARM-2518 | Deschutes Fleet Services Maintenance Facility | Lucas Bennett | 2026-06-27 15:15 | High | 1296000 | 2523000 | Current field plan and committed buyout reflected. | Received
ARM-2522 | Summit Surgical Center Central Plant | Elliot Marks | 2026-06-26 17:15 | High | 1982000 | 3424000 | Current field plan and committed buyout reflected. | Received
ARM-2526 | Willamette Food Co-op Refrigeration Upgrade | Sofia Alvarez | 2026-06-25 17:15 | High | 347000 | 1370000 | Current field plan and committed buyout reflected. | Received
ARM-2602 | Pacific NW Distribution Center Heat Recovery | Priya Raman | 2026-06-26 17:15 | High | 3644000 | 4455000 | Current field plan and committed buyout reflected. | Received
ARM-2605 | Rose Quarter Event Level Ventilation | Elliot Marks | 2026-06-24 16:15 | Medium | 4124000 | 4782000 | Current field plan and committed buyout reflected. | Received
ARM-2608 | Cascade Health Imaging Suite Controls | Sofia Alvarez | 2026-06-27 15:15 | High | 881000 | 1396000 | Current field plan and committed buyout reflected. | Received

## Project Forecasts
PM Forecast Detail
Component build and PM-entered assumptions as submitted; Finance review is outside this workbook
Project ID | Remaining Field Labor | Material / Equipment | Subcontract | Commissioning & Close-out | Contingency | Project-specific Exposure | Forecast Credit / (Offset) | Forecast ETC | Assumption Reference | Confidence | Project Manager | Narrative
ARM-2318 | 62568 | 53878 | 31284 | 15642 | 10428 | 0 | 0 | 173800 | PM submission | Medium | Maya Chen | Forecast based on CV-2318-06 and open PO-2318-102.
ARM-2403 | 321120 | 276520 | 160560 | 80280 | 53520 | 0 | 0 | 892000 | PM submission | High | Elliot Marks | Current field plan and committed buyout reflected.
ARM-2409 | 210240 | 181040 | 105120 | 52560 | 35040 | 185000 | -185000 | 584000 | PCO-011 working estimate | Low | Priya Raman | Forecast refreshed in the weekly project review and submitted 2026-06-28.
ARM-2412 | 340920 | 293570 | 170460 | 85230 | 56820 | 0 | 0 | 947000 | PM submission | High | Elliot Marks | Current field plan and committed buyout reflected.
ARM-2417 | 1097280 | 944880 | 548640 | 274320 | 182880 | 0 | 0 | 3048000 | PM submission | Low | Maya Chen | Forecast based on phasing Rev 5 and open commitments through 6/24.
ARM-2421 | 11160 | 9610 | 5580 | 2790 | 1860 | 0 | 0 | 31000 | PM submission | High | Lucas Bennett | Current field plan and committed buyout reflected.
ARM-2501 | 329040 | 283340 | 164520 | 82260 | 54840 | 0 | 0 | 914000 | PM submission | High | Sofia Alvarez | Current field plan and committed buyout reflected.
ARM-2506 | 1703160 | 1466610 | 851580 | 425790 | 283860 | 0 | 0 | 4731000 | PM submission | Low | Priya Raman | Forecast based on IFC package E-18 and commitments through 6/24.
ARM-2510 | 1182240 | 1018040 | 591120 | 295560 | 197040 | 0 | 0 | 3284000 | PM submission | High | Maya Chen | Current field plan and committed buyout reflected.
ARM-2514 | 537120 | 462520 | 268560 | 134280 | 89520 | 0 | 0 | 1492000 | PM submission | High | Lucas Bennett | Current field plan and committed buyout reflected.
ARM-2518 | 466560 | 401760 | 233280 | 116640 | 77760 | 0 | 0 | 1296000 | PM submission | High | Lucas Bennett | Current field plan and committed buyout reflected.
ARM-2522 | 713520 | 614420 | 356760 | 178380 | 118920 | 0 | 0 | 1982000 | PM submission | High | Elliot Marks | Current field plan and committed buyout reflected.
ARM-2526 | 124920 | 107570 | 62460 | 31230 | 20820 | 0 | 0 | 347000 | PM submission | High | Sofia Alvarez | Current field plan and committed buyout reflected.
ARM-2602 | 1311840 | 1129640 | 655920 | 327960 | 218640 | 0 | 0 | 3644000 | PM submission | High | Priya Raman | Current field plan and committed buyout reflected.
ARM-2605 | 1484640 | 1278440 | 742320 | 371160 | 247440 | 0 | 0 | 4124000 | PM submission | Medium | Elliot Marks | Current field plan and committed buyout reflected.
ARM-2608 | 317160 | 273110 | 158580 | 79290 | 52860 | 0 | 0 | 881000 | PM submission | High | Sofia Alvarez | Current field plan and committed buyout reflected.

## Commitment Detail
Open Commitment Detail
Project forecast module export through 2026-06-28 ¦ Operations Finance working file
Project ID | Commitment Ref | Vendor / Trade | Work Package | Cost Bucket | Open Commitment | PM Forecast Amount | PM Status | Last Updated
ARM-2318 | PO-2318-102 | Columbia Rigging Services | Process-skid equipment lift | Subcontract | 22750 | 22750 | Open at PM snapshot | 2026-06-27
ARM-2318 | SC-2318-08 | High Desert Insulation | Insulation closeout | Subcontract | 8534 | 8534 | Open at PM snapshot | 2026-06-26
ARM-2403 | SC-2403-02 | Cascade Controls Integration | controls completion | Subcontract | 77069 | 77069 | Open at PM snapshot | 2026-06-25
ARM-2403 | SC-2403-09 | Pacific Test & Balance | commissioning support | Subcontract | 83491 | 83491 | Open at PM snapshot | 2026-06-24
ARM-2409 | PO-2409-117 | Rogue Valley Sheet Metal Fabrication - Bend LLC | Freezer-slab mechanical rework | Subcontract | 33796.69 | 46800 | Open at PM snapshot | 2026-06-27
ARM-2409 | SC-2409-08 | Cascade Controls Integration | Controls completion and turnover | Subcontract | 58320 | 58320 | Open at PM snapshot | 2026-06-27
ARM-2412 | SC-2412-04 | Pacific Test & Balance | commissioning support | Subcontract | 71593 | 71593 | Open at PM snapshot | 2026-06-27
ARM-2412 | SC-2412-11 | Evergreen Mechanical Supply | remaining material | Subcontract | 98867 | 98867 | Open at PM snapshot | 2026-06-26
ARM-2417 | SC-2417-05 | Columbia Rigging Services | equipment setting | Subcontract | 263347 | 263347 | Awaiting final field quantity | 2026-06-28
ARM-2417 | SC-2417-12 | Northwest Pipe & Valve | equipment and trim | Subcontract | 285293 | 285293 | Open at PM snapshot | 2026-06-27
ARM-2421 | SC-2421-06 | Evergreen Mechanical Supply | remaining material | Subcontract | 3013 | 3013 | Open at PM snapshot | 2026-06-24
ARM-2421 | SC-2421-13 | Cascade Controls Integration | controls completion | Subcontract | 2567 | 2567 | Open at PM snapshot | 2026-06-28
ARM-2501 | SC-2501-07 | Northwest Pipe & Valve | equipment and trim | Subcontract | 69098 | 69098 | Open at PM snapshot | 2026-06-25
ARM-2501 | SC-2501-14 | High Desert Insulation | insulation closeout | Subcontract | 95422 | 95422 | Open at PM snapshot | 2026-06-23
ARM-2506 | SC-2506-01 | Cascade Controls Integration | controls completion | Subcontract | 408758 | 408758 | Open at PM snapshot | 2026-06-26
ARM-2506 | SC-2506-08 | Pacific Test & Balance | commissioning support | Subcontract | 442822 | 442822 | Open at PM snapshot | 2026-06-24
ARM-2510 | SC-2510-02 | High Desert Insulation | insulation closeout | Subcontract | 319205 | 319205 | Awaiting final field quantity | 2026-06-27
ARM-2510 | SC-2510-09 | Columbia Rigging Services | equipment setting | Subcontract | 271915 | 271915 | Open at PM snapshot | 2026-06-25
ARM-2514 | SC-2514-03 | Pacific Test & Balance | commissioning support | Subcontract | 112795 | 112795 | Open at PM snapshot | 2026-06-28
ARM-2514 | SC-2514-10 | Evergreen Mechanical Supply | remaining material | Subcontract | 155765 | 155765 | Open at PM snapshot | 2026-06-26
ARM-2518 | SC-2518-04 | Columbia Rigging Services | equipment setting | Subcontract | 111974 | 111974 | Open at PM snapshot | 2026-06-24
ARM-2518 | SC-2518-11 | Northwest Pipe & Valve | equipment and trim | Subcontract | 121306 | 121306 | Open at PM snapshot | 2026-06-27
ARM-2522 | SC-2522-11 | Prime Electric & Controls | Electrical subcontract completion | Subcontract | 96000 | 96000 | Open at PM snapshot | 2026-06-28
ARM-2522 | SC-2522-14 | Pacific Test & Balance | Testing and commissioning balance | Subcontract | 260760 | 260760 | Open at PM snapshot | 2026-06-27
ARM-2526 | SC-2526-06 | Northwest Pipe & Valve | equipment and trim | Subcontract | 26233 | 26233 | Awaiting final field quantity | 2026-06-26
ARM-2526 | SC-2526-13 | High Desert Insulation | insulation closeout | Subcontract | 36227 | 36227 | Open at PM snapshot | 2026-06-23
ARM-2602 | SC-2602-07 | Cascade Controls Integration | controls completion | Subcontract | 314842 | 314842 | Open at PM snapshot | 2026-06-27
ARM-2602 | SC-2602-14 | Pacific Test & Balance | commissioning support | Subcontract | 341078 | 341078 | Open at PM snapshot | 2026-06-24
ARM-2605 | SC-2605-01 | High Desert Insulation | insulation closeout | Subcontract | 400853 | 400853 | Open at PM snapshot | 2026-06-28
ARM-2605 | SC-2605-08 | Columbia Rigging Services | equipment setting | Subcontract | 341467 | 341467 | Open at PM snapshot | 2026-06-25
ARM-2608 | SC-2608-02 | Pacific Test & Balance | commissioning support | Subcontract | 66604 | 66604 | Open at PM snapshot | 2026-06-24
ARM-2608 | SC-2608-09 | Evergreen Mechanical Supply | remaining material | Subcontract | 91976 | 91976 | Open at PM snapshot | 2026-06-26

## Risks & Opportunities
Risks, Opportunities and Unpriced Exposure
Working PM register; current status and support must be verified in the commercial file
Project ID | Reference | Description | Revenue Opportunity | Cost Exposure / (Recovery) | Commercial Status | Probability | Last Updated | Owner
ARM-2417 | PCO-017 | OR congestion and after-hours premium | 382000 | 275000 | Submitted | 75% | 2026-06-17 | Maya Chen
ARM-2409 | PCO-011 | Freezer slab rework backcharge to concrete trade | 185000 | -185000 | Draft | 40% | 2026-06-24 | Priya Raman
ARM-2506 | PCO-006 | Chiller electrical service redesign | 296000 | 210000 | Pricing | 80% | 2026-06-21 | Priya Raman
ARM-2514 | CO-008 | Gym ventilation scope revision | 214000 | 147000 | Approved | 100% | 2026-06-12 | Lucas Bennett
ARM-2318 | PCO-029 | Final validation retest and extended support | 68000 | 45000 | Submitted | 65% | 2026-06-27 | Maya Chen
ARM-2605 | PCO-002 | Temporary ventilation for summer events | 174000 | 121000 | Under Review | 25% | 2026-06-28 | Elliot Marks
ARM-2403 | CO-014 | AHU-4 controls sequence revision | 96000 | 62000 | Approved | 100% | 2026-05-19 | Elliot Marks
ARM-2412 | CO-009 | Lab exhaust fan VFD replacements | 133000 | 88000 | Approved | 100% | 2026-06-03 | Elliot Marks

## Instructions & Sign-off
Forecast Submission Protocol
Operations Finance ¦ Rev. 2026-03
Submission steps
1 | Update remaining labor, material, subcontract, commissioning, close-out and contingency from the current field plan.
2 | Enter project-specific exposures and forecast credits separately rather than inside another component.
3 | Reference the supporting commercial or project file for each non-routine assumption.
4 | Keep each risk or opportunity on a separate register line until the underlying matter is resolved.
5 | Do not overwrite posted actual cost or billing fields in a PM submission.
6 | Retain the submitted timestamp, PM name and confidence assessment.
7 | Finance applies the current close policy and documents any accounting adjustment outside this workbook.

## PM inputs - raw
Combined from individual PM files and two e-mail replies at 5:30pm 6/29. Timestamps differ because some files were resaved by Ops Finance.
job_no | pm | submitted | etc_from_pm | confidence typed | comment copied | source filename | Ops Fin note
ARM-2318 | Maya Chen | 2026-06-27 15:15 | 173800 | medium | Forecast based on CV-2318-06 and open PO-2318-102. | ARM-2318_Maya_ETC_final.xlsx | manual copy - formulas removed
ARM-2403 | Elliot Marks | 2026-06-27 18:15 | 892000 | High | Current field plan and committed buyout reflected. | ARM-2403_Elliot_ETC_v2.xlsx | linked then pasted values
ARM-2409 | Priya Raman | 2026-06-28 16:15 | 584000 | Low | Forecast refreshed in the weekly project review and submitted 2026-06-28. | ARM-2409_Priya_ETC_6.29.xlsx | linked then pasted values
ARM-2412 | Elliot Marks | 2026-06-26 17:15 | 947000 | High | Current field plan and committed buyout reflected. | ARM-2412_Elliot_ETC_USE THIS.xlsx | linked then pasted values
ARM-2417 | Maya Chen | 2026-06-26 18:15 | 3048000 | low | Forecast based on phasing Rev 5 and open commitments through 6/24. | ARM-2417_Maya_ETC_final.xlsx | linked then pasted values
ARM-2421 | Lucas Bennett | 2026-06-25 16:15 | 31000 | High | Current field plan and committed buyout reflected. | ARM-2421_Lucas_ETC_v2.xlsx | manual copy - formulas removed
ARM-2501 | Sofia Alvarez | 2026-06-25 16:15 | 914000 | High | Current field plan and committed buyout reflected. | ARM-2501_Sofia_ETC_6.29.xlsx | linked then pasted values
ARM-2506 | Priya Raman | 2026-06-25 17:15 | 4731000 | Low | Forecast based on IFC package E-18 and commitments through 6/24. | ARM-2506_Priya_ETC_USE THIS.xlsx | linked then pasted values
ARM-2510 | Maya Chen | 2026-06-24 15:15 | 3284000 | high | Current field plan and committed buyout reflected. | ARM-2510_Maya_ETC_final.xlsx | linked then pasted values
ARM-2514 | Lucas Bennett | 2026-06-28 15:15 | 1492000 | High | Current field plan and committed buyout reflected. | ARM-2514_Lucas_ETC_v2.xlsx | linked then pasted values
ARM-2518 | Lucas Bennett | 2026-06-27 15:15 | 1296000 | High | Current field plan and committed buyout reflected. | ARM-2518_Lucas_ETC_6.29.xlsx | manual copy - formulas removed
ARM-2522 | Elliot Marks | 2026-06-26 17:15 | 1982000 | High | Current field plan and committed buyout reflected. | ARM-2522_Elliot_ETC_USE THIS.xlsx | linked then pasted values
ARM-2526 | Sofia Alvarez | 2026-06-25 17:15 | 347000 | high | Current field plan and committed buyout reflected. | ARM-2526_Sofia_ETC_final.xlsx | linked then pasted values
ARM-2602 | Priya Raman | 2026-06-26 17:15 | 3644000 | High | Current field plan and committed buyout reflected. | ARM-2602_Priya_ETC_v2.xlsx | linked then pasted values
ARM-2605 | Elliot Marks | 2026-06-24 16:15 | 4124000 | Medium | Current field plan and committed buyout reflected. | ARM-2605_Elliot_ETC_6.29.xlsx | linked then pasted values
ARM-2608 | Sofia Alvarez | 2026-06-27 15:15 | 881000 | High | Current field plan and committed buyout reflected. | ARM-2608_Sofia_ETC_USE THIS.xlsx | manual copy - formulas removed

## old roll fwd
Copied from May combined file. Kept because Submission Register formulas used to reference columns C/F; no longer authoritative.
Job | May ETC | June placeholder | delta | old flag | May reviewer note
ARM-2318 | 167543 | 173800 | 6257 | FOLLOW UP | waiting on quote
ARM-2403 | 875944 | 892000 | 16056 |  | crew plan updated
ARM-2409 | 584000 | 584000 | 0 |  | closeout only
ARM-2412 | 964046 | 947000 | -17046 |  | carry prior until PM reply
ARM-2417 | 3157728 | 3048000 | -109728 |  | waiting on quote
ARM-2421 | 29884 | 31000 | 1116 |  | crew plan updated
ARM-2501 | 897548 | 914000 | 16452 | FOLLOW UP | closeout only
ARM-2506 | 4731000 | 4731000 | 0 |  | carry prior until PM reply
ARM-2510 | 3343112 | 3284000 | -59112 |  | waiting on quote
ARM-2514 | 1545712 | 1492000 | -53712 |  | crew plan updated
ARM-2518 | 1249344 | 1296000 | 46656 |  | closeout only
ARM-2522 | 1946324 | 1982000 | 35676 |  | carry prior until PM reply
ARM-2526 | 347000 | 347000 | 0 | FOLLOW UP | waiting on quote
ARM-2602 | 3709592 | 3644000 | -65592 |  | crew plan updated
ARM-2605 | 4272464 | 4124000 | -148464 |  | closeout only
ARM-2608 | 849284 | 881000 | 31716 |  | carry prior until PM reply