## Contract Backlog
Complete the backlog burn and capacity model ¦ Contract Backlog
LOCKED INPUT SCHEDULE • refreshed from current management workbooks and Vista ERP • Do not edit
Source Ref | Schedule | Entity | Period | Scenario | Measure | Numeric Value | Text Value | Unit | Source Document | Source Date | System Tie
035-SRC0001 | Signed contract backlog | P-3101 | 2026-06-30 | Approved case | Remaining transaction price | 8400000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0002 | Signed contract backlog | P-3101 | FY27 | Approved case | Contract start month |  | 2026-07 | classification | Finance operating schedule | 2026-06-30
035-SRC0003 | Signed contract backlog | P-3101 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0004 | Signed contract backlog | P-3101 | FY27 | Approved case | Revenue per productive hour | 118 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0008 | Project burn curve | P-3101 | 2026-07 | Approved case | Monthly burn share | 0.012821 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0009 | Project burn curve | P-3101 | 2026-08 | Approved case | Monthly burn share | 0.025641 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0010 | Project burn curve | P-3101 | 2026-09 | Approved case | Monthly burn share | 0.038462 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0011 | Project burn curve | P-3101 | 2026-10 | Approved case | Monthly burn share | 0.051282 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0012 | Project burn curve | P-3101 | 2026-11 | Approved case | Monthly burn share | 0.064103 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0013 | Project burn curve | P-3101 | 2026-12 | Approved case | Monthly burn share | 0.076923 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0014 | Project burn curve | P-3101 | 2027-01 | Approved case | Monthly burn share | 0.089744 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0015 | Project burn curve | P-3101 | 2027-02 | Approved case | Monthly burn share | 0.10256 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0016 | Project burn curve | P-3101 | 2027-03 | Approved case | Monthly burn share | 0.11538 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0017 | Project burn curve | P-3101 | 2027-04 | Approved case | Monthly burn share | 0.12821 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0018 | Project burn curve | P-3101 | 2027-05 | Approved case | Monthly burn share | 0.14103 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0019 | Project burn curve | P-3101 | 2027-06 | Approved case | Monthly burn share | 0.15385 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0020 | Signed contract backlog | P-3107 | 2026-06-30 | Approved case | Remaining transaction price | 6900 |  | USD thousands | Finance operating schedule | 2026-06-30
035-SRC0021 | Signed contract backlog | P-3107 | FY27 | Approved case | Contract start month |  | 2026-08 | classification | Finance operating schedule | 2026-06-30
035-SRC0022 | Signed contract backlog | P-3107 | FY27 | Approved case | Execution probability | 0.95 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0023 | Signed contract backlog | P-3107 | FY27 | Approved case | Revenue per productive hour | 126 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0027 | Project burn curve | P-3107 | 2026-08 | Approved case | Monthly burn share | 0.015152 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0028 | Project burn curve | P-3107 | 2026-09 | Approved case | Monthly burn share | 0.030303 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0029 | Project burn curve | P-3107 | 2026-10 | Approved case | Monthly burn share | 0.045455 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0030 | Project burn curve | P-3107 | 2026-11 | Approved case | Monthly burn share | 0.060606 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0031 | Project burn curve | P-3107 | 2026-12 | Approved case | Monthly burn share | 0.075758 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0032 | Project burn curve | P-3107 | 2027-01 | Approved case | Monthly burn share | 0.090909 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0033 | Project burn curve | P-3107 | 2027-02 | Approved case | Monthly burn share | 0.10606 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0034 | Project burn curve | P-3107 | 2027-03 | Approved case | Monthly burn share | 0.12121 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0035 | Project burn curve | P-3107 | 2027-04 | Approved case | Monthly burn share | 0.13636 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0036 | Project burn curve | P-3107 | 2027-05 | Approved case | Monthly burn share | 0.15152 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0037 | Project burn curve | P-3107 | 2027-06 | Approved case | Monthly burn share | 0.16667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0038 | Signed contract backlog | P-3114 | 2026-06-30 | Approved case | Remaining transaction price | 5600000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0039 | Signed contract backlog | P-3114 | FY27 | Approved case | Contract start month |  | 2026-10 | classification | Finance operating schedule | 2026-06-30
035-SRC0040 | Signed contract backlog | P-3114 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0041 | Signed contract backlog | P-3114 | FY27 | Approved case | Revenue per productive hour | 132 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0045 | Project burn curve | P-3114 | 2026-10 | Approved case | Monthly burn share | 0.022222 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0046 | Project burn curve | P-3114 | 2026-11 | Approved case | Monthly burn share | 0.044444 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0047 | Project burn curve | P-3114 | 2026-12 | Approved case | Monthly burn share | 0.066667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0048 | Project burn curve | P-3114 | 2027-01 | Approved case | Monthly burn share | 0.088889 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0049 | Project burn curve | P-3114 | 2027-02 | Approved case | Monthly burn share | 0.11111 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0050 | Project burn curve | P-3114 | 2027-03 | Approved case | Monthly burn share | 0.13333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0051 | Project burn curve | P-3114 | 2027-04 | Approved case | Monthly burn share | 0.15556 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0052 | Project burn curve | P-3114 | 2027-05 | Approved case | Monthly burn share | 0.17778 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0053 | Project burn curve | P-3114 | 2027-06 | Approved case | Monthly burn share | 0.2 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0054 | Signed contract backlog | P-3122 | 2026-06-30 | Approved case | Remaining transaction price | 4750000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0055 | Signed contract backlog | P-3122 | FY27 | Approved case | Contract start month |  | 2026-12 | classification | Finance operating schedule | 2026-06-30
035-SRC0056 | Signed contract backlog | P-3122 | FY27 | Approved case | Execution probability | 0.85 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0057 | Signed contract backlog | P-3122 | FY27 | Approved case | Revenue per productive hour | 120 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0061 | Project burn curve | P-3122 | 2026-12 | Approved case | Monthly burn share | 0.035714 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0062 | Project burn curve | P-3122 | 2027-01 | Approved case | Monthly burn share | 0.071429 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0063 | Project burn curve | P-3122 | 2027-02 | Approved case | Monthly burn share | 0.10714 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0064 | Project burn curve | P-3122 | 2027-03 | Approved case | Monthly burn share | 0.14286 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0065 | Project burn curve | P-3122 | 2027-04 | Approved case | Monthly burn share | 0.17857 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0066 | Project burn curve | P-3122 | 2027-05 | Approved case | Monthly burn share | 0.21429 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0067 | Project burn curve | P-3122 | 2027-06 | Approved case | Monthly burn share | 0.25 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0068 | Signed contract backlog | P-3130 | 2026-06-30 | Approved case | Remaining transaction price | 7200 |  | USD thousands | Finance operating schedule | 2026-06-30
035-SRC0069 | Signed contract backlog | P-3130 | FY27 | Approved case | Contract start month |  | 2027-01 | classification | Finance operating schedule | 2026-06-30
035-SRC0070 | Signed contract backlog | P-3130 | FY27 | Approved case | Execution probability | 0.9 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0071 | Signed contract backlog | P-3130 | FY27 | Approved case | Revenue per productive hour | 138 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0075 | Project burn curve | P-3130 | 2027-01 | Approved case | Monthly burn share | 0.047619 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0076 | Project burn curve | P-3130 | 2027-02 | Approved case | Monthly burn share | 0.095238 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0077 | Project burn curve | P-3130 | 2027-03 | Approved case | Monthly burn share | 0.14286 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0078 | Project burn curve | P-3130 | 2027-04 | Approved case | Monthly burn share | 0.19048 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0079 | Project burn curve | P-3130 | 2027-05 | Approved case | Monthly burn share | 0.2381 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0080 | Project burn curve | P-3130 | 2027-06 | Approved case | Monthly burn share | 0.28571 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0081 | Signed contract backlog | P-3138 | 2026-06-30 | Approved case | Remaining transaction price | 3900000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0082 | Signed contract backlog | P-3138 | FY27 | Approved case | Contract start month |  | 2027-02 | classification | Finance operating schedule | 2026-06-30
035-SRC0083 | Signed contract backlog | P-3138 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0084 | Signed contract backlog | P-3138 | FY27 | Approved case | Revenue per productive hour | 125 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0088 | Project burn curve | P-3138 | 2027-02 | Approved case | Monthly burn share | 0.066667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0089 | Project burn curve | P-3138 | 2027-03 | Approved case | Monthly burn share | 0.13333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0090 | Project burn curve | P-3138 | 2027-04 | Approved case | Monthly burn share | 0.2 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0091 | Project burn curve | P-3138 | 2027-05 | Approved case | Monthly burn share | 0.26667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0092 | Project burn curve | P-3138 | 2027-06 | Approved case | Monthly burn share | 0.33333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0093 | Signed contract backlog | P-3145 | 2026-06-30 | Approved case | Remaining transaction price | 5100000 |  | USD | Finance operating schedule | 2026-06-30
035-SRC0094 | Signed contract backlog | P-3145 | FY27 | Approved case | Contract start month |  | 2027-03 | classification | Finance operating schedule | 2026-06-30
035-SRC0095 | Signed contract backlog | P-3145 | FY27 | Approved case | Execution probability | 0.8 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0096 | Signed contract backlog | P-3145 | FY27 | Approved case | Revenue per productive hour | 145 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0100 | Project burn curve | P-3145 | 2027-03 | Approved case | Monthly burn share | 0.1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0101 | Project burn curve | P-3145 | 2027-04 | Approved case | Monthly burn share | 0.2 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0102 | Project burn curve | P-3145 | 2027-05 | Approved case | Monthly burn share | 0.3 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0103 | Project burn curve | P-3145 | 2027-06 | Approved case | Monthly burn share | 0.4 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0104 | Signed contract backlog | P-3152 | 2026-06-30 | Approved case | Remaining transaction price | 2850 |  | USD thousands | Finance operating schedule | 2026-06-30
035-SRC0105 | Signed contract backlog | P-3152 | FY27 | Approved case | Contract start month |  | 2027-04 | classification | Finance operating schedule | 2026-06-30
035-SRC0106 | Signed contract backlog | P-3152 | FY27 | Approved case | Execution probability | 1 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0107 | Signed contract backlog | P-3152 | FY27 | Approved case | Revenue per productive hour | 130 |  | USD per hour | Finance operating schedule | 2026-06-30
035-SRC0111 | Project burn curve | P-3152 | 2027-04 | Approved case | Monthly burn share | 0.16667 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0112 | Project burn curve | P-3152 | 2027-05 | Approved case | Monthly burn share | 0.33333 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0113 | Project burn curve | P-3152 | 2027-06 | Approved case | Monthly burn share | 0.5 |  | decimal ratio | Finance operating schedule | 2026-06-30

## Capacity Inputs
Complete the backlog burn and capacity model ¦ Capacity Inputs
LOCKED INPUT SCHEDULE • refreshed from current management workbooks and Vista ERP • Do not edit
Source Ref | Schedule | Entity | Period | Scenario | Measure | Numeric Value | Text Value | Unit | Source Document | Source Date | System Tie
035-SRC0114 | Monthly capacity | All field labor | 2026-07 | Approved case | Productive internal hours | 31500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0115 | Monthly capacity | All field labor | 2026-07 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0116 | Monthly capacity | All field labor | 2026-07 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0117 | Capacity remediation | All field labor | 2026-07 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0118 | Capacity remediation | All field labor | 2026-07 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0119 | Capacity remediation | All field labor | 2026-07 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0120 | Capacity remediation | All field labor | 2026-07 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0121 | Monthly capacity | All field labor | 2026-08 | Approved case | Productive internal hours | 31780 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0122 | Monthly capacity | All field labor | 2026-08 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0123 | Monthly capacity | All field labor | 2026-08 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0124 | Capacity remediation | All field labor | 2026-08 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0125 | Capacity remediation | All field labor | 2026-08 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0126 | Capacity remediation | All field labor | 2026-08 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0127 | Capacity remediation | All field labor | 2026-08 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0128 | Monthly capacity | All field labor | 2026-09 | Approved case | Productive internal hours | 32060 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0129 | Monthly capacity | All field labor | 2026-09 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0130 | Monthly capacity | All field labor | 2026-09 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0131 | Capacity remediation | All field labor | 2026-09 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0132 | Capacity remediation | All field labor | 2026-09 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0133 | Capacity remediation | All field labor | 2026-09 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0134 | Capacity remediation | All field labor | 2026-09 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0135 | Monthly capacity | All field labor | 2026-10 | Approved case | Productive internal hours | 32340 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0136 | Monthly capacity | All field labor | 2026-10 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0137 | Monthly capacity | All field labor | 2026-10 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0138 | Capacity remediation | All field labor | 2026-10 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0139 | Capacity remediation | All field labor | 2026-10 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0140 | Capacity remediation | All field labor | 2026-10 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0141 | Capacity remediation | All field labor | 2026-10 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0142 | Monthly capacity | All field labor | 2026-11 | Approved case | Productive internal hours | 32620 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0143 | Monthly capacity | All field labor | 2026-11 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0144 | Monthly capacity | All field labor | 2026-11 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0145 | Capacity remediation | All field labor | 2026-11 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0146 | Capacity remediation | All field labor | 2026-11 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0147 | Capacity remediation | All field labor | 2026-11 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0148 | Capacity remediation | All field labor | 2026-11 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0149 | Monthly capacity | All field labor | 2026-12 | Approved case | Productive internal hours | 30100 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0150 | Monthly capacity | All field labor | 2026-12 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0151 | Monthly capacity | All field labor | 2026-12 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0152 | Capacity remediation | All field labor | 2026-12 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0153 | Capacity remediation | All field labor | 2026-12 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0154 | Capacity remediation | All field labor | 2026-12 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0155 | Capacity remediation | All field labor | 2026-12 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0156 | Monthly capacity | All field labor | 2027-01 | Approved case | Productive internal hours | 30380 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0157 | Monthly capacity | All field labor | 2027-01 | Approved case | Subcontractable hours | 4500 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0158 | Monthly capacity | All field labor | 2027-01 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0159 | Capacity remediation | All field labor | 2027-01 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0160 | Capacity remediation | All field labor | 2027-01 | Approved case | Contingent subcontract surge hours | 2500 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0161 | Capacity remediation | All field labor | 2027-01 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0162 | Capacity remediation | All field labor | 2027-01 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0163 | Monthly capacity | All field labor | 2027-02 | Approved case | Productive internal hours | 33460 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0164 | Monthly capacity | All field labor | 2027-02 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0165 | Monthly capacity | All field labor | 2027-02 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0166 | Capacity remediation | All field labor | 2027-02 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0167 | Capacity remediation | All field labor | 2027-02 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0168 | Capacity remediation | All field labor | 2027-02 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0169 | Capacity remediation | All field labor | 2027-02 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0170 | Monthly capacity | All field labor | 2027-03 | Approved case | Productive internal hours | 33740 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0171 | Monthly capacity | All field labor | 2027-03 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0172 | Monthly capacity | All field labor | 2027-03 | Approved case | Overtime limit on internal hours | 0.05 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0173 | Capacity remediation | All field labor | 2027-03 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0174 | Capacity remediation | All field labor | 2027-03 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0175 | Capacity remediation | All field labor | 2027-03 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0176 | Capacity remediation | All field labor | 2027-03 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0177 | Monthly capacity | All field labor | 2027-04 | Approved case | Productive internal hours | 34020 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0178 | Monthly capacity | All field labor | 2027-04 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0179 | Monthly capacity | All field labor | 2027-04 | Approved case | Overtime limit on internal hours | 0.05 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0180 | Capacity remediation | All field labor | 2027-04 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0181 | Capacity remediation | All field labor | 2027-04 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0182 | Capacity remediation | All field labor | 2027-04 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0183 | Capacity remediation | All field labor | 2027-04 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0184 | Monthly capacity | All field labor | 2027-05 | Approved case | Productive internal hours | 34300 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0185 | Monthly capacity | All field labor | 2027-05 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0186 | Monthly capacity | All field labor | 2027-05 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0187 | Capacity remediation | All field labor | 2027-05 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0188 | Capacity remediation | All field labor | 2027-05 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0189 | Capacity remediation | All field labor | 2027-05 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0190 | Capacity remediation | All field labor | 2027-05 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30
035-SRC0191 | Monthly capacity | All field labor | 2027-06 | Approved case | Productive internal hours | 34580 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0192 | Monthly capacity | All field labor | 2027-06 | Approved case | Subcontractable hours | 3200 |  | hours | Finance operating schedule | 2026-06-30
035-SRC0193 | Monthly capacity | All field labor | 2027-06 | Approved case | Overtime limit on internal hours | 0.08 |  | decimal ratio | Finance operating schedule | 2026-06-30
035-SRC0194 | Capacity remediation | All field labor | 2027-06 | Approved case | Emergency overtime increment limit | 0.04 |  | decimal ratio | Approved capacity-response policy | 2026-06-30
035-SRC0195 | Capacity remediation | All field labor | 2027-06 | Approved case | Contingent subcontract surge hours | 4000 |  | hours | Executed contingent labor framework | 2026-06-30
035-SRC0196 | Capacity remediation | All field labor | 2027-06 | Approved case | Overtime premium cost | 42.5 |  | USD per hour | Approved labor-cost assumptions | 2026-06-30
035-SRC0197 | Capacity remediation | All field labor | 2027-06 | Approved case | Contingent subcontract cost | 125 |  | USD per hour | Executed contingent labor framework | 2026-06-30

## Execution Authority
Complete the backlog burn and capacity model ¦ Execution Authority
LOCKED INPUT SCHEDULE • refreshed from current management workbooks and Vista ERP • Do not edit
Source Ref | Schedule | Entity | Period | Scenario | Measure | Numeric Value | Text Value | Unit | Source Document | Source Date | System Tie
035-SRC0005 | Execution authority | P-3101 | FY27 | Approved case | Customer delivery priority | 1 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0006 | Execution authority | P-3101 | FY27 | Approved case | Contract gross margin | 0.24 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0007 | Execution authority | P-3101 | FY27 | Approved case | Monthly liquidated damages rate | 0.006 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0024 | Execution authority | P-3107 | FY27 | Approved case | Customer delivery priority | 2 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0025 | Execution authority | P-3107 | FY27 | Approved case | Contract gross margin | 0.22 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0026 | Execution authority | P-3107 | FY27 | Approved case | Monthly liquidated damages rate | 0.008 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0042 | Execution authority | P-3114 | FY27 | Approved case | Customer delivery priority | 1 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0043 | Execution authority | P-3114 | FY27 | Approved case | Contract gross margin | 0.27 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0044 | Execution authority | P-3114 | FY27 | Approved case | Monthly liquidated damages rate | 0.007 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0058 | Execution authority | P-3122 | FY27 | Approved case | Customer delivery priority | 3 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0059 | Execution authority | P-3122 | FY27 | Approved case | Contract gross margin | 0.2 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0060 | Execution authority | P-3122 | FY27 | Approved case | Monthly liquidated damages rate | 0.01 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0072 | Execution authority | P-3130 | FY27 | Approved case | Customer delivery priority | 2 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0073 | Execution authority | P-3130 | FY27 | Approved case | Contract gross margin | 0.25 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0074 | Execution authority | P-3130 | FY27 | Approved case | Monthly liquidated damages rate | 0.009 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0085 | Execution authority | P-3138 | FY27 | Approved case | Customer delivery priority | 4 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0086 | Execution authority | P-3138 | FY27 | Approved case | Contract gross margin | 0.18 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0087 | Execution authority | P-3138 | FY27 | Approved case | Monthly liquidated damages rate | 0.012 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0097 | Execution authority | P-3145 | FY27 | Approved case | Customer delivery priority | 3 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0098 | Execution authority | P-3145 | FY27 | Approved case | Contract gross margin | 0.29 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0099 | Execution authority | P-3145 | FY27 | Approved case | Monthly liquidated damages rate | 0.011 |  | decimal ratio | Executed contract terms | 2026-06-30
035-SRC0108 | Execution authority | P-3152 | FY27 | Approved case | Customer delivery priority | 4 |  | priority rank | Approved project-execution register | 2026-06-30
035-SRC0109 | Execution authority | P-3152 | FY27 | Approved case | Contract gross margin | 0.17 |  | decimal ratio | Controller-approved project economics | 2026-06-30
035-SRC0110 | Execution authority | P-3152 | FY27 | Approved case | Monthly liquidated damages rate | 0.014 |  | decimal ratio | Executed contract terms | 2026-06-30

## Revenue Burn
Complete the backlog burn and capacity model ¦ Revenue Burn
WORKING MODEL • link calculations to supporting schedules and complete the control section
Required headline output | Formula-driven result
signed_backlog
fy27_backlog_revenue_burn
2026_07_revenue_burn
2026_08_revenue_burn
2026_09_revenue_burn
2026_10_revenue_burn
2026_11_revenue_burn
2026_12_revenue_burn
2027_01_revenue_burn
2027_02_revenue_burn
2027_03_revenue_burn
2027_04_revenue_burn
2027_05_revenue_burn
2027_06_revenue_burn
gross_commitment_2026_07_revenue_burn
gross_commitment_2026_08_revenue_burn
gross_commitment_2026_09_revenue_burn
gross_commitment_2026_10_revenue_burn
gross_commitment_2026_11_revenue_burn
gross_commitment_2026_12_revenue_burn
gross_commitment_2027_01_revenue_burn
gross_commitment_2027_02_revenue_burn
gross_commitment_2027_03_revenue_burn
gross_commitment_2027_04_revenue_burn
gross_commitment_2027_05_revenue_burn
gross_commitment_2027_06_revenue_burn
gross_commitment_revenue_burn
Period / Scenario | Business unit / item | Metric | Input / driver | Formula output | Unit | Source / file / ref | Check

## Labor Capacity
Complete the backlog burn and capacity model ¦ Labor Capacity
WORKING MODEL • link calculations to supporting schedules and complete the control section
Required headline output | Formula-driven result
fy27_required_hours
fy27_available_hours
2026_07_required_hours
2026_07_productive_internal_hours
2026_07_permitted_overtime_hours
2026_07_subcontractable_hours
2026_07_available_hours
2026_07_remediated_available_hours
2026_08_required_hours
2026_08_productive_internal_hours
2026_08_permitted_overtime_hours
2026_08_subcontractable_hours
2026_08_available_hours
2026_08_remediated_available_hours
2026_09_required_hours
2026_09_productive_internal_hours
2026_09_permitted_overtime_hours
2026_09_subcontractable_hours
2026_09_available_hours
2026_09_remediated_available_hours
2026_10_required_hours
2026_10_productive_internal_hours
2026_10_permitted_overtime_hours
2026_10_subcontractable_hours
2026_10_available_hours
2026_10_remediated_available_hours
2026_11_required_hours
2026_11_productive_internal_hours
2026_11_permitted_overtime_hours
2026_11_subcontractable_hours
2026_11_available_hours
2026_11_remediated_available_hours
2026_12_required_hours
2026_12_productive_internal_hours
2026_12_permitted_overtime_hours
2026_12_subcontractable_hours
2026_12_available_hours
2026_12_remediated_available_hours
2027_01_required_hours
2027_01_productive_internal_hours
2027_01_permitted_overtime_hours
2027_01_subcontractable_hours
2027_01_available_hours
2027_01_remediated_available_hours
2027_02_required_hours
2027_02_productive_internal_hours
2027_02_permitted_overtime_hours
2027_02_subcontractable_hours
2027_02_available_hours
2027_02_remediated_available_hours
2027_03_required_hours
2027_03_productive_internal_hours
2027_03_permitted_overtime_hours
2027_03_subcontractable_hours
2027_03_available_hours
2027_03_remediated_available_hours
2027_04_required_hours
2027_04_productive_internal_hours
2027_04_permitted_overtime_hours
2027_04_subcontractable_hours
2027_04_available_hours
2027_04_remediated_available_hours
2027_05_required_hours
2027_05_productive_internal_hours
2027_05_permitted_overtime_hours
2027_05_subcontractable_hours
2027_05_available_hours
2027_05_remediated_available_hours
2027_06_required_hours
2027_06_productive_internal_hours
2027_06_permitted_overtime_hours
2027_06_subcontractable_hours
2027_06_available_hours
2027_06_remediated_available_hours
gross_commitment_2026_07_required_hours
gross_commitment_2026_08_required_hours
gross_commitment_2026_09_required_hours
gross_commitment_2026_10_required_hours
gross_commitment_2026_11_required_hours
gross_commitment_2026_12_required_hours
gross_commitment_2027_01_required_hours
gross_commitment_2027_02_required_hours
gross_commitment_2027_03_required_hours
gross_commitment_2027_04_required_hours
gross_commitment_2027_05_required_hours
gross_commitment_2027_06_required_hours
gross_commitment_required_hours
Period / Scenario | Business unit / item | Metric | Input / driver | Formula output | Unit | Source / file / ref | Check

## Gap Analysis
Complete the backlog burn and capacity model ¦ Gap Analysis
WORKING MODEL • link calculations to supporting schedules and complete the control section
Required headline output | Formula-driven result
constrained_month_count
first_constrained_month
maximum_capacity_shortfall_hours
2026_07_capacity_gap_hours
2026_07_base_capacity_shortfall
2026_07_emergency_overtime_capacity
2026_07_emergency_overtime_deployed
2026_07_shortfall_after_emergency_overtime
2026_07_contingent_subcontract_capacity
2026_07_contingent_subcontract_deployed
2026_07_unresolved_capacity_shortfall
2026_07_remediated_available_hours
2026_07_incremental_remediation_cost
2026_07_capacity_release_status
2026_08_capacity_gap_hours
2026_08_base_capacity_shortfall
2026_08_emergency_overtime_capacity
2026_08_emergency_overtime_deployed
2026_08_shortfall_after_emergency_overtime
2026_08_contingent_subcontract_capacity
2026_08_contingent_subcontract_deployed
2026_08_unresolved_capacity_shortfall
2026_08_remediated_available_hours
2026_08_incremental_remediation_cost
2026_08_capacity_release_status
2026_09_capacity_gap_hours
2026_09_base_capacity_shortfall
2026_09_emergency_overtime_capacity
2026_09_emergency_overtime_deployed
2026_09_shortfall_after_emergency_overtime
2026_09_contingent_subcontract_capacity
2026_09_contingent_subcontract_deployed
2026_09_unresolved_capacity_shortfall
2026_09_remediated_available_hours
2026_09_incremental_remediation_cost
2026_09_capacity_release_status
2026_10_capacity_gap_hours
2026_10_base_capacity_shortfall
2026_10_emergency_overtime_capacity
2026_10_emergency_overtime_deployed
2026_10_shortfall_after_emergency_overtime
2026_10_contingent_subcontract_capacity
2026_10_contingent_subcontract_deployed
2026_10_unresolved_capacity_shortfall
2026_10_remediated_available_hours
2026_10_incremental_remediation_cost
2026_10_capacity_release_status
2026_11_capacity_gap_hours
2026_11_base_capacity_shortfall
2026_11_emergency_overtime_capacity
2026_11_emergency_overtime_deployed
2026_11_shortfall_after_emergency_overtime
2026_11_contingent_subcontract_capacity
2026_11_contingent_subcontract_deployed
2026_11_unresolved_capacity_shortfall
2026_11_remediated_available_hours
2026_11_incremental_remediation_cost
2026_11_capacity_release_status
2026_12_capacity_gap_hours
2026_12_base_capacity_shortfall
2026_12_emergency_overtime_capacity
2026_12_emergency_overtime_deployed
2026_12_shortfall_after_emergency_overtime
2026_12_contingent_subcontract_capacity
2026_12_contingent_subcontract_deployed
2026_12_unresolved_capacity_shortfall
2026_12_remediated_available_hours
2026_12_incremental_remediation_cost
2026_12_capacity_release_status
2027_01_capacity_gap_hours
2027_01_base_capacity_shortfall
2027_01_emergency_overtime_capacity
2027_01_emergency_overtime_deployed
2027_01_shortfall_after_emergency_overtime
2027_01_contingent_subcontract_capacity
2027_01_contingent_subcontract_deployed
2027_01_unresolved_capacity_shortfall
2027_01_remediated_available_hours
2027_01_incremental_remediation_cost
2027_01_capacity_release_status
2027_02_capacity_gap_hours
2027_02_base_capacity_shortfall
2027_02_emergency_overtime_capacity
2027_02_emergency_overtime_deployed
2027_02_shortfall_after_emergency_overtime
2027_02_contingent_subcontract_capacity
2027_02_contingent_subcontract_deployed
2027_02_unresolved_capacity_shortfall
2027_02_remediated_available_hours
2027_02_incremental_remediation_cost
2027_02_capacity_release_status
2027_03_capacity_gap_hours
2027_03_base_capacity_shortfall
2027_03_emergency_overtime_capacity
2027_03_emergency_overtime_deployed
2027_03_shortfall_after_emergency_overtime
2027_03_contingent_subcontract_capacity
2027_03_contingent_subcontract_deployed
2027_03_unresolved_capacity_shortfall
2027_03_remediated_available_hours
2027_03_incremental_remediation_cost
2027_03_capacity_release_status
2027_04_capacity_gap_hours
2027_04_base_capacity_shortfall
2027_04_emergency_overtime_capacity
2027_04_emergency_overtime_deployed
2027_04_shortfall_after_emergency_overtime
2027_04_contingent_subcontract_capacity
2027_04_contingent_subcontract_deployed
2027_04_unresolved_capacity_shortfall
2027_04_remediated_available_hours
2027_04_incremental_remediation_cost
2027_04_capacity_release_status
2027_05_capacity_gap_hours
2027_05_base_capacity_shortfall
2027_05_emergency_overtime_capacity
2027_05_emergency_overtime_deployed
2027_05_shortfall_after_emergency_overtime
2027_05_contingent_subcontract_capacity
2027_05_contingent_subcontract_deployed
2027_05_unresolved_capacity_shortfall
2027_05_remediated_available_hours
2027_05_incremental_remediation_cost
2027_05_capacity_release_status
2027_06_capacity_gap_hours
2027_06_base_capacity_shortfall
2027_06_emergency_overtime_capacity
2027_06_emergency_overtime_deployed
2027_06_shortfall_after_emergency_overtime
2027_06_contingent_subcontract_capacity
2027_06_contingent_subcontract_deployed
2027_06_unresolved_capacity_shortfall
2027_06_remediated_available_hours
2027_06_incremental_remediation_cost
2027_06_capacity_release_status
gross_commitment_2026_07_base_capacity_shortfall
gross_commitment_2026_07_emergency_overtime_deployed
gross_commitment_2026_07_shortfall_after_emergency_overtime
gross_commitment_2026_07_contingent_subcontract_deployed
gross_commitment_2026_07_unresolved_capacity_shortfall
gross_commitment_2026_07_incremental_remediation_cost
gross_commitment_2026_07_capacity_release_status
gross_commitment_2026_08_base_capacity_shortfall
gross_commitment_2026_08_emergency_overtime_deployed
gross_commitment_2026_08_shortfall_after_emergency_overtime
gross_commitment_2026_08_contingent_subcontract_deployed
gross_commitment_2026_08_unresolved_capacity_shortfall
gross_commitment_2026_08_incremental_remediation_cost
gross_commitment_2026_08_capacity_release_status
gross_commitment_2026_09_base_capacity_shortfall
gross_commitment_2026_09_emergency_overtime_deployed
gross_commitment_2026_09_shortfall_after_emergency_overtime
gross_commitment_2026_09_contingent_subcontract_deployed
gross_commitment_2026_09_unresolved_capacity_shortfall
gross_commitment_2026_09_incremental_remediation_cost
gross_commitment_2026_09_capacity_release_status
gross_commitment_2026_10_base_capacity_shortfall
gross_commitment_2026_10_emergency_overtime_deployed
gross_commitment_2026_10_shortfall_after_emergency_overtime
gross_commitment_2026_10_contingent_subcontract_deployed
gross_commitment_2026_10_unresolved_capacity_shortfall
gross_commitment_2026_10_incremental_remediation_cost
gross_commitment_2026_10_capacity_release_status
gross_commitment_2026_11_base_capacity_shortfall
gross_commitment_2026_11_emergency_overtime_deployed
gross_commitment_2026_11_shortfall_after_emergency_overtime
gross_commitment_2026_11_contingent_subcontract_deployed
gross_commitment_2026_11_unresolved_capacity_shortfall
gross_commitment_2026_11_incremental_remediation_cost
gross_commitment_2026_11_capacity_release_status
gross_commitment_2026_12_base_capacity_shortfall
gross_commitment_2026_12_emergency_overtime_deployed
gross_commitment_2026_12_shortfall_after_emergency_overtime
gross_commitment_2026_12_contingent_subcontract_deployed
gross_commitment_2026_12_unresolved_capacity_shortfall
gross_commitment_2026_12_incremental_remediation_cost
gross_commitment_2026_12_capacity_release_status
gross_commitment_2027_01_base_capacity_shortfall
gross_commitment_2027_01_emergency_overtime_deployed
gross_commitment_2027_01_shortfall_after_emergency_overtime
gross_commitment_2027_01_contingent_subcontract_deployed
gross_commitment_2027_01_unresolved_capacity_shortfall
gross_commitment_2027_01_incremental_remediation_cost
gross_commitment_2027_01_capacity_release_status
gross_commitment_2027_02_base_capacity_shortfall
gross_commitment_2027_02_emergency_overtime_deployed
gross_commitment_2027_02_shortfall_after_emergency_overtime
gross_commitment_2027_02_contingent_subcontract_deployed
gross_commitment_2027_02_unresolved_capacity_shortfall
gross_commitment_2027_02_incremental_remediation_cost
gross_commitment_2027_02_capacity_release_status
gross_commitment_2027_03_base_capacity_shortfall
gross_commitment_2027_03_emergency_overtime_deployed
gross_commitment_2027_03_shortfall_after_emergency_overtime
gross_commitment_2027_03_contingent_subcontract_deployed
gross_commitment_2027_03_unresolved_capacity_shortfall
gross_commitment_2027_03_incremental_remediation_cost
gross_commitment_2027_03_capacity_release_status
gross_commitment_2027_04_base_capacity_shortfall
gross_commitment_2027_04_emergency_overtime_deployed
gross_commitment_2027_04_shortfall_after_emergency_overtime
gross_commitment_2027_04_contingent_subcontract_deployed
gross_commitment_2027_04_unresolved_capacity_shortfall
gross_commitment_2027_04_incremental_remediation_cost
gross_commitment_2027_04_capacity_release_status
gross_commitment_2027_05_base_capacity_shortfall
gross_commitment_2027_05_emergency_overtime_deployed
gross_commitment_2027_05_shortfall_after_emergency_overtime
gross_commitment_2027_05_contingent_subcontract_deployed
gross_commitment_2027_05_unresolved_capacity_shortfall
gross_commitment_2027_05_incremental_remediation_cost
gross_commitment_2027_05_capacity_release_status
gross_commitment_2027_06_base_capacity_shortfall
gross_commitment_2027_06_emergency_overtime_deployed
gross_commitment_2027_06_shortfall_after_emergency_overtime
gross_commitment_2027_06_contingent_subcontract_deployed
gross_commitment_2027_06_unresolved_capacity_shortfall
gross_commitment_2027_06_incremental_remediation_cost
gross_commitment_2027_06_capacity_release_status
Period / Scenario | Business unit / item | Metric | Input / driver | Formula output | Unit | Source / file / ref | Check

## Project Execution
Complete the backlog burn and capacity model ¦ Project Execution
WORKING MODEL • link calculations to supporting schedules and complete the control section
Required headline output | Formula-driven result
execution_2026_07_available_hours
execution_2026_07_due_hours
execution_2026_07_completed_hours
execution_2026_07_ending_deferred_hours
execution_2026_07_capacity_utilization
execution_2026_07_completed_revenue
execution_2026_07_ending_deferred_revenue
execution_2026_07_completed_gross_profit
execution_2026_07_liquidated_damages
execution_2026_07_release_status
release_bridge_2026_07_probability_plan_gross_profit_before_remediation
release_bridge_2026_07_probability_plan_remediation_cost
release_bridge_2026_07_probability_plan_gross_profit_after_remediation
release_bridge_2026_07_gross_commitment_gross_profit_before_remediation
release_bridge_2026_07_gross_commitment_remediation_cost
release_bridge_2026_07_gross_commitment_gross_profit_after_remediation
release_bridge_2026_07_incremental_gross_profit_after_remediation
release_bridge_2026_07_execution_net_gross_profit_after_damages
release_bridge_2026_07_deferred_revenue_at_risk
release_bridge_2026_07_management_release_status
execution_2026_08_available_hours
execution_2026_08_due_hours
execution_2026_08_completed_hours
execution_2026_08_ending_deferred_hours
execution_2026_08_capacity_utilization
execution_2026_08_completed_revenue
execution_2026_08_ending_deferred_revenue
execution_2026_08_completed_gross_profit
execution_2026_08_liquidated_damages
execution_2026_08_release_status
release_bridge_2026_08_probability_plan_gross_profit_before_remediation
release_bridge_2026_08_probability_plan_remediation_cost
release_bridge_2026_08_probability_plan_gross_profit_after_remediation
release_bridge_2026_08_gross_commitment_gross_profit_before_remediation
release_bridge_2026_08_gross_commitment_remediation_cost
release_bridge_2026_08_gross_commitment_gross_profit_after_remediation
release_bridge_2026_08_incremental_gross_profit_after_remediation
release_bridge_2026_08_execution_net_gross_profit_after_damages
release_bridge_2026_08_deferred_revenue_at_risk
release_bridge_2026_08_management_release_status
execution_2026_09_available_hours
execution_2026_09_due_hours
execution_2026_09_completed_hours
execution_2026_09_ending_deferred_hours
execution_2026_09_capacity_utilization
execution_2026_09_completed_revenue
execution_2026_09_ending_deferred_revenue
execution_2026_09_completed_gross_profit
execution_2026_09_liquidated_damages
execution_2026_09_release_status
release_bridge_2026_09_probability_plan_gross_profit_before_remediation
release_bridge_2026_09_probability_plan_remediation_cost
release_bridge_2026_09_probability_plan_gross_profit_after_remediation
release_bridge_2026_09_gross_commitment_gross_profit_before_remediation
release_bridge_2026_09_gross_commitment_remediation_cost
release_bridge_2026_09_gross_commitment_gross_profit_after_remediation
release_bridge_2026_09_incremental_gross_profit_after_remediation
release_bridge_2026_09_execution_net_gross_profit_after_damages
release_bridge_2026_09_deferred_revenue_at_risk
release_bridge_2026_09_management_release_status
execution_2026_10_available_hours
execution_2026_10_due_hours
execution_2026_10_completed_hours
execution_2026_10_ending_deferred_hours
execution_2026_10_capacity_utilization
execution_2026_10_completed_revenue
execution_2026_10_ending_deferred_revenue
execution_2026_10_completed_gross_profit
execution_2026_10_liquidated_damages
execution_2026_10_release_status
release_bridge_2026_10_probability_plan_gross_profit_before_remediation
release_bridge_2026_10_probability_plan_remediation_cost
release_bridge_2026_10_probability_plan_gross_profit_after_remediation
release_bridge_2026_10_gross_commitment_gross_profit_before_remediation
release_bridge_2026_10_gross_commitment_remediation_cost
release_bridge_2026_10_gross_commitment_gross_profit_after_remediation
release_bridge_2026_10_incremental_gross_profit_after_remediation
release_bridge_2026_10_execution_net_gross_profit_after_damages
release_bridge_2026_10_deferred_revenue_at_risk
release_bridge_2026_10_management_release_status
execution_2026_11_available_hours
execution_2026_11_due_hours
execution_2026_11_completed_hours
execution_2026_11_ending_deferred_hours
execution_2026_11_capacity_utilization
execution_2026_11_completed_revenue
execution_2026_11_ending_deferred_revenue
execution_2026_11_completed_gross_profit
execution_2026_11_liquidated_damages
execution_2026_11_release_status
release_bridge_2026_11_probability_plan_gross_profit_before_remediation
release_bridge_2026_11_probability_plan_remediation_cost
release_bridge_2026_11_probability_plan_gross_profit_after_remediation
release_bridge_2026_11_gross_commitment_gross_profit_before_remediation
release_bridge_2026_11_gross_commitment_remediation_cost
release_bridge_2026_11_gross_commitment_gross_profit_after_remediation
release_bridge_2026_11_incremental_gross_profit_after_remediation
release_bridge_2026_11_execution_net_gross_profit_after_damages
release_bridge_2026_11_deferred_revenue_at_risk
release_bridge_2026_11_management_release_status
execution_2026_12_available_hours
execution_2026_12_due_hours
execution_2026_12_completed_hours
execution_2026_12_ending_deferred_hours
execution_2026_12_capacity_utilization
execution_2026_12_completed_revenue
execution_2026_12_ending_deferred_revenue
execution_2026_12_completed_gross_profit
execution_2026_12_liquidated_damages
execution_2026_12_release_status
release_bridge_2026_12_probability_plan_gross_profit_before_remediation
release_bridge_2026_12_probability_plan_remediation_cost
release_bridge_2026_12_probability_plan_gross_profit_after_remediation
release_bridge_2026_12_gross_commitment_gross_profit_before_remediation
release_bridge_2026_12_gross_commitment_remediation_cost
release_bridge_2026_12_gross_commitment_gross_profit_after_remediation
release_bridge_2026_12_incremental_gross_profit_after_remediation
release_bridge_2026_12_execution_net_gross_profit_after_damages
release_bridge_2026_12_deferred_revenue_at_risk
release_bridge_2026_12_management_release_status
execution_2027_01_available_hours
execution_2027_01_due_hours
execution_2027_01_completed_hours
execution_2027_01_ending_deferred_hours
execution_2027_01_capacity_utilization
execution_2027_01_completed_revenue
execution_2027_01_ending_deferred_revenue
execution_2027_01_completed_gross_profit
execution_2027_01_liquidated_damages
execution_2027_01_release_status
release_bridge_2027_01_probability_plan_gross_profit_before_remediation
release_bridge_2027_01_probability_plan_remediation_cost
release_bridge_2027_01_probability_plan_gross_profit_after_remediation
release_bridge_2027_01_gross_commitment_gross_profit_before_remediation
release_bridge_2027_01_gross_commitment_remediation_cost
release_bridge_2027_01_gross_commitment_gross_profit_after_remediation
release_bridge_2027_01_incremental_gross_profit_after_remediation
release_bridge_2027_01_execution_net_gross_profit_after_damages
release_bridge_2027_01_deferred_revenue_at_risk
release_bridge_2027_01_management_release_status
execution_2027_02_available_hours
execution_2027_02_due_hours
execution_2027_02_completed_hours
execution_2027_02_ending_deferred_hours
execution_2027_02_capacity_utilization
execution_2027_02_completed_revenue
execution_2027_02_ending_deferred_revenue
execution_2027_02_completed_gross_profit
execution_2027_02_liquidated_damages
execution_2027_02_release_status
release_bridge_2027_02_probability_plan_gross_profit_before_remediation
release_bridge_2027_02_probability_plan_remediation_cost
release_bridge_2027_02_probability_plan_gross_profit_after_remediation
release_bridge_2027_02_gross_commitment_gross_profit_before_remediation
release_bridge_2027_02_gross_commitment_remediation_cost
release_bridge_2027_02_gross_commitment_gross_profit_after_remediation
release_bridge_2027_02_incremental_gross_profit_after_remediation
release_bridge_2027_02_execution_net_gross_profit_after_damages
release_bridge_2027_02_deferred_revenue_at_risk
release_bridge_2027_02_management_release_status
execution_2027_03_available_hours
execution_2027_03_due_hours
execution_2027_03_completed_hours
execution_2027_03_ending_deferred_hours
execution_2027_03_capacity_utilization
execution_2027_03_completed_revenue
execution_2027_03_ending_deferred_revenue
execution_2027_03_completed_gross_profit
execution_2027_03_liquidated_damages
execution_2027_03_release_status
release_bridge_2027_03_probability_plan_gross_profit_before_remediation
release_bridge_2027_03_probability_plan_remediation_cost
release_bridge_2027_03_probability_plan_gross_profit_after_remediation
release_bridge_2027_03_gross_commitment_gross_profit_before_remediation
release_bridge_2027_03_gross_commitment_remediation_cost
release_bridge_2027_03_gross_commitment_gross_profit_after_remediation
release_bridge_2027_03_incremental_gross_profit_after_remediation
release_bridge_2027_03_execution_net_gross_profit_after_damages
release_bridge_2027_03_deferred_revenue_at_risk
release_bridge_2027_03_management_release_status
execution_2027_04_available_hours
execution_2027_04_due_hours
execution_2027_04_completed_hours
execution_2027_04_ending_deferred_hours
execution_2027_04_capacity_utilization
execution_2027_04_completed_revenue
execution_2027_04_ending_deferred_revenue
execution_2027_04_completed_gross_profit
execution_2027_04_liquidated_damages
execution_2027_04_release_status
release_bridge_2027_04_probability_plan_gross_profit_before_remediation
release_bridge_2027_04_probability_plan_remediation_cost
release_bridge_2027_04_probability_plan_gross_profit_after_remediation
release_bridge_2027_04_gross_commitment_gross_profit_before_remediation
release_bridge_2027_04_gross_commitment_remediation_cost
release_bridge_2027_04_gross_commitment_gross_profit_after_remediation
release_bridge_2027_04_incremental_gross_profit_after_remediation
release_bridge_2027_04_execution_net_gross_profit_after_damages
release_bridge_2027_04_deferred_revenue_at_risk
release_bridge_2027_04_management_release_status
execution_2027_05_available_hours
execution_2027_05_due_hours
execution_2027_05_completed_hours
execution_2027_05_ending_deferred_hours
execution_2027_05_capacity_utilization
execution_2027_05_completed_revenue
execution_2027_05_ending_deferred_revenue
execution_2027_05_completed_gross_profit
execution_2027_05_liquidated_damages
execution_2027_05_release_status
release_bridge_2027_05_probability_plan_gross_profit_before_remediation
release_bridge_2027_05_probability_plan_remediation_cost
release_bridge_2027_05_probability_plan_gross_profit_after_remediation
release_bridge_2027_05_gross_commitment_gross_profit_before_remediation
release_bridge_2027_05_gross_commitment_remediation_cost
release_bridge_2027_05_gross_commitment_gross_profit_after_remediation
release_bridge_2027_05_incremental_gross_profit_after_remediation
release_bridge_2027_05_execution_net_gross_profit_after_damages
release_bridge_2027_05_deferred_revenue_at_risk
release_bridge_2027_05_management_release_status
execution_2027_06_available_hours
execution_2027_06_due_hours
execution_2027_06_completed_hours
execution_2027_06_ending_deferred_hours
execution_2027_06_capacity_utilization
execution_2027_06_completed_revenue
execution_2027_06_ending_deferred_revenue
execution_2027_06_completed_gross_profit
execution_2027_06_liquidated_damages
execution_2027_06_release_status
release_bridge_2027_06_probability_plan_gross_profit_before_remediation
release_bridge_2027_06_probability_plan_remediation_cost
release_bridge_2027_06_probability_plan_gross_profit_after_remediation
release_bridge_2027_06_gross_commitment_gross_profit_before_remediation
release_bridge_2027_06_gross_commitment_remediation_cost
release_bridge_2027_06_gross_commitment_gross_profit_after_remediation
release_bridge_2027_06_incremental_gross_profit_after_remediation
release_bridge_2027_06_execution_net_gross_profit_after_damages
release_bridge_2027_06_deferred_revenue_at_risk
release_bridge_2027_06_management_release_status
execution_p_3114_customer_delivery_priority
execution_p_3114_contract_gross_margin
execution_p_3114_monthly_liquidated_damages_rate
execution_p_3114_signed_backlog
execution_p_3114_completed_hours
execution_p_3114_completed_revenue
execution_p_3114_ending_deferred_hours
execution_p_3114_ending_deferred_revenue
execution_p_3114_completed_gross_profit
execution_p_3114_liquidated_damages
execution_p_3114_net_gross_profit_after_damages
execution_p_3114_release_status
execution_p_3101_customer_delivery_priority
execution_p_3101_contract_gross_margin
execution_p_3101_monthly_liquidated_damages_rate
execution_p_3101_signed_backlog
execution_p_3101_completed_hours
execution_p_3101_completed_revenue
execution_p_3101_ending_deferred_hours
execution_p_3101_ending_deferred_revenue
execution_p_3101_completed_gross_profit
execution_p_3101_liquidated_damages
execution_p_3101_net_gross_profit_after_damages
execution_p_3101_release_status
execution_p_3130_customer_delivery_priority
execution_p_3130_contract_gross_margin
execution_p_3130_monthly_liquidated_damages_rate
execution_p_3130_signed_backlog
execution_p_3130_completed_hours
execution_p_3130_completed_revenue
execution_p_3130_ending_deferred_hours
execution_p_3130_ending_deferred_revenue
execution_p_3130_completed_gross_profit
execution_p_3130_liquidated_damages
execution_p_3130_net_gross_profit_after_damages
execution_p_3130_release_status
execution_p_3107_customer_delivery_priority
execution_p_3107_contract_gross_margin
execution_p_3107_monthly_liquidated_damages_rate
execution_p_3107_signed_backlog
execution_p_3107_completed_hours
execution_p_3107_completed_revenue
execution_p_3107_ending_deferred_hours
execution_p_3107_ending_deferred_revenue
execution_p_3107_completed_gross_profit
execution_p_3107_liquidated_damages
execution_p_3107_net_gross_profit_after_damages
execution_p_3107_release_status
execution_p_3145_customer_delivery_priority
execution_p_3145_contract_gross_margin
execution_p_3145_monthly_liquidated_damages_rate
execution_p_3145_signed_backlog
execution_p_3145_completed_hours
execution_p_3145_completed_revenue
execution_p_3145_ending_deferred_hours
execution_p_3145_ending_deferred_revenue
execution_p_3145_completed_gross_profit
execution_p_3145_liquidated_damages
execution_p_3145_net_gross_profit_after_damages
execution_p_3145_release_status
execution_p_3122_customer_delivery_priority
execution_p_3122_contract_gross_margin
execution_p_3122_monthly_liquidated_damages_rate
execution_p_3122_signed_backlog
execution_p_3122_completed_hours
execution_p_3122_completed_revenue
execution_p_3122_ending_deferred_hours
execution_p_3122_ending_deferred_revenue
execution_p_3122_completed_gross_profit
execution_p_3122_liquidated_damages
execution_p_3122_net_gross_profit_after_damages
execution_p_3122_release_status
execution_p_3152_customer_delivery_priority
execution_p_3152_contract_gross_margin
execution_p_3152_monthly_liquidated_damages_rate
execution_p_3152_signed_backlog
execution_p_3152_completed_hours
execution_p_3152_completed_revenue
execution_p_3152_ending_deferred_hours
execution_p_3152_ending_deferred_revenue
execution_p_3152_completed_gross_profit
execution_p_3152_liquidated_damages
execution_p_3152_net_gross_profit_after_damages
execution_p_3152_release_status
execution_p_3138_customer_delivery_priority
execution_p_3138_contract_gross_margin
execution_p_3138_monthly_liquidated_damages_rate
execution_p_3138_signed_backlog
execution_p_3138_completed_hours
execution_p_3138_completed_revenue
execution_p_3138_ending_deferred_hours
execution_p_3138_ending_deferred_revenue
execution_p_3138_completed_gross_profit
execution_p_3138_liquidated_damages
execution_p_3138_net_gross_profit_after_damages
execution_p_3138_release_status
execution_portfolio_completed_revenue
execution_portfolio_ending_deferred_revenue
execution_portfolio_revenue_check_delta
execution_portfolio_ending_deferred_hours
execution_portfolio_completed_gross_profit
execution_portfolio_liquidated_damages
execution_portfolio_net_gross_profit_after_damages
execution_portfolio_highest_priority_deferred_project
execution_portfolio_release_status
release_bridge_probability_plan_gross_profit_after_remediation
release_bridge_gross_commitment_gross_profit_after_remediation
release_bridge_execution_net_gross_profit_after_damages
release_bridge_deferred_revenue_at_risk
release_bridge_management_decision
executive_recovery_probability_plan_gp_after_remediation
executive_recovery_gross_commitment_gp_after_remediation
executive_recovery_execution_net_gp_after_damages
executive_recovery_probability_plan_variance
executive_recovery_gross_commitment_shortfall
executive_recovery_deferred_revenue_at_risk
executive_recovery_deferred_gross_profit_at_risk
executive_recovery_liquidated_damages
executive_recovery_required_recovery
executive_recovery_highest_priority_deferred_project
executive_recovery_required_action
executive_recovery_release_condition
executive_recovery_decision
Period / Scenario | Business unit / item | Metric | Input / driver | Formula output | Unit | Source / file / ref | Check

## Checks
Complete the backlog burn and capacity model ¦ Checks
WORKING MODEL • link calculations to supporting schedules and complete the control section
Check | Actual | Expected | Difference | Tolerance | Status | Where to fix / source
Source population tie
Current-versus-prior version
Period completeness
Scenario validity
Unit conversion
Roll-forward / bridge
MODEL STATUS